SCOPE OF WORK FOR

DRILLING, SONIC CORING, AND CONSTRUCTION

OF ONE EWDP PHASE V MONITORING WELL

### 1.0  Introduction

The scope of work encompasses all activities associated with the drilling, sonic coring, and construction of a dual string piezometer monitor well to a total depth of 650 ft below ground surface (bgs) in Fortymile Wash alluvial sediments at a location approximately 5 miles northwest of Lathrop Wells, NV.  This well will be located approximately 60 ft due west of existing well number 19IM1 shown in Figure 1.

This single EWDP borehole will only penetrate relatively coarse grained alluvium.  The alluvium will include alternating thin (sometimes less than 2.5 ft thick) layers of relatively clean sand and gravel, sand and gravel with silt and/or clay, and silty sand with gravel.  A summary lithologic log for a well located approximately 120 ft from the well proposed herein is presented in Figure 2.  Some loss of bentonite drilling fluids (11,500 to 14,000 gallons) were observed while drilling the upper approximately 350 ft of two previous boreholes at this location using flooded mud reverse circulation methods.  The water table is expected to be encountered at approximately 360 ft bgs.

It is expected the Contractor will use two drill rigs, one for drilling and casing of the unsaturated alluvium, and one for the Sonic coring and borehole advancement in saturated alluvium.  However, if available, a multipurpose rig with all the required capabilities will of course be acceptable.  The drill site has been graded and fenced by the Nye County Nuclear Waste Repository Project Office (NWRPO).  The Contractor will be responsible for digging pits for liquid drilling fluids/cuttings.

The NWRPO and the Department of Energy contractors (DOE) will be responsible for maintaining depth control through pipe tally records.  Pipe tally records will be kept for all drilling, coring, and completion activities.  The Contractor will cooperate with the NWRPO and DOE in maintaining these records.

Contractor responsibilities regarding drilling permits required by the state of Nevada Department of Water Resources, waste disposal, health and safety, training, fire prevention, spill prevention and cleanup, good drilling/completion operation practices, supply of electricity and water, handling of nuisance water, water sampling,  use of drilling fluids and lubricants, and other miscellaneous activities/requirements are described in Part V, Sections A and B of this document (Drilling, Sonic Coring, and Construction of One EWDP Phase V Monitoring Well – Bid Specifications and Request for Proposal).  In addition, communication and record keeping responsibilities for both the Contactor and the NWRPO are listed in Section B of Part V.  Finally, equipment and material specifications are described in Part V Sections C and D.

Detailed specifications and requirements regarding mobilization/demobilization, drilling and casing of unsaturated alluvium, continuous Sonic coring of saturated alluvium, selected drive coring of saturated alluvium, borehole geophysical logging, subsurface completion of a dual piezometer monitor well, and the surface completion of this well are presented in the following.

- Mobilization/Demobilization

  - The rig(s), auxiliary equipment, drillpipe and other downhole equipment and tools shall be mobilized in a clean condition, generally free of surface grease, soil, or other potential contaminants.  Steam cleaning of grease, dirt, etc., from previous jobs not related to the subject work on NWRPO locations will not be allowed.

  - Mobilization will be considered complete when all of the items listed in Part V, Section B, Item 2 have been accomplished.

  - Demobilization will be considered complete when:

- Tasks specified in the contract are completed or exempted from completion with approval of the NWRPO.

- All personnel, equipment, tools, unused materials, and drilling related debris are removed from the drill site location as well as the NWRPO laydown yard in Lathrop Wells.  In addition, any pits and berms on the drill site must be graded to approximately the original elevation.

# Proposed Drilling and Casing of Unsaturated Alluvium

Using conventional rotary, dual rotary, or another proven drilling method, drill a suitable borehole and install an approximately 9-inch diameter (or larger) conductor casing to a depth of 350 ft bgs (approximately 10 ft above the water table) in accordance with specifications listed below.  The Contractor may elect to drill a borehole significantly larger in diameter (e.g. >12-inches) than the conductor casing and then grout the casing in place with concrete grout, or the Contractor may choose to drill the conductor casing to 350 ft bgs using a drilling method such as dual rotary.

  - Regardless of the drilling method employed, permissible drilling fluids are limited to water, untreated bentonite mud (e.g. AQUA GEL GOLD SEAL),  and compressed air.  The Contractor must obtain NWRPO approval before using any other drilling fluid or additive.

  - The Contractor must employ methods (e.g. drilling collars) to keep the borehole deviation from exceeding 2 degrees from vertical at 350 ft bgs.  In addition, no “dog legs” are permitted where deviation exceeds 0.5 degrees per 100 ft.  The Contractor must conduct a deviation survey at 350 ft bgs to demonstrate the first requirement.  If there appears to be a significant dog-leg, the NWRPO will conduct a survey to determine if the second requirement is met.

  - If the Contractor elects to use conventional rotary drilling methods and concrete grout the approximately 9-inch conductor casing in place, the borehole must be drilled to at least 12-inch in diameter to 350 ft bgs.  The concrete grout must be pumped through a tremmie pipe using a “bottom-up” approach in stages to prevent casing collapse.  In addition, the Contractor may also want to set a larger diameter surface casing (temporary or permanent) to prevent near surface caving of unconsolidated coarse grained sediments.

  - If the Contractor chooses to drill the approximately 9-inch conductor casing to down to 350 ft bgs using a drilling method such as dual rotary, the contractor must first permanently install a larger diameter steel surface casing to at least 60 ft bgs.  The diameter of the upper 60 ft of borehole and the diameter of the steel surface casing must be sufficient to permit grouting the surface casing with concrete and to support dual  rotary drilling of the approximately 9-inch conductor casing to 350 ft bgs.

4.0  Sonic Coring of Saturated Alluvium

4.1	Run in approximately 8-inch diameter steel drill casing inside the approximately 9-           inch conductor casing to 350 ft bgs.

4.2	Run in approximately 15 ft of approximately 6-inch steel core barrel attached to smaller diameter drill rods to 350 ft bgs.

4.3	Advance the approximately 6-inch core barrel using Sonic methods to a maximum target depth 10 ft below the approximately 8-inch drill casing.  In some cases the core barrel will meet refusal before 10 ft is reached.  When the target depth of 10 ft is reached or the when barrel meets refusal at a depth of less than 10 ft, return the core barrel to the ground surface and transfer the core sample to approximately 2 foot lengths of  4 to 6 mil polyethylene tubing.  NWRPO and DOE will be responsible for determining and labeling the depth intervals of each approximately 2 ft length of core in polyethylene tubing.

4.4	If the necessary 10 ft target depth was not reached on the above core run, run the approximately 6-inch core barrel back into the bore hole and continue advancing it to a depth 10 ft ahead of the approximately 8-inch drill casing.  At this point, use Sonic methods to advance the 8-inch drill casing down to the bottom of the borehole using the approximately 6-inch core barrel to clean out sediments from inside the drill casing.  Remove the cleanout sediments from the borehole and core barrel prior to advancing the approximately 6-inch core barrel as described in section 4.3 above.  Prior to each advance with the 6-inch core barrel, the bottom of hole will be sounded with a tagging tool and the core barrel will be empty, thus simplifying the determination of the length of core sample vs. the length of cleanout material collected in the core barrel.

Continue collecting approximately 6-inch Sonic core and advancing the approximately 8-inch drill casing until (in the opinion of the Contractor) it is no longer feasible to do so.  This depth of advancement must be greater than or equal to 450 ft bgs and not exceed 650 ft bgs.  It is realistically expected that the maximum depth of advancement of this drilling/coring system will be between 450 and 550 ft bgs. For the purpose of the Cost Consideration Schedule (Table 1) in Part I, Section C of this document, it will be assumed that the 6-inch core barrel and 8-inch drill casing will be advanced from 350 to 500 ft bgs.

4.5	When advancement is no longer feasible with the above drilling/coring system, remove the approximately 6-inch Sonic core barrel and run in an approximately 5.5-inch drill casing and an approximately 3.5-inch core barrel.  Continue collecting continuous Sonic core and advancing the borehole in a similar manner as sections 4.3 and 4.4 above using this smaller drilling/coring system to a maximum depth of 650 ft bgs.

For the purpose of the Cost Consideration Schedule (Table 1) in Part I, Section C of this document, it will be assumed that the approximately 5.5-inch drill casing and the approximately 3.5-inch core barrel will be advanced from 500 to 650 ft bgs.

5.0  Drive Coring of Selected Intervals of Saturated Alluvium

The NWRPO will supply solid tube samplers, brass liners to fit inside the samplers, and necessary cross-over subs to connect to the Contractors percussion hammer.  The contractor will supply drill rod, a 5-inch air percussion hammer, and a 350 psi and 900 cfm compressor. The drive coring program will involve collecting 2 ft long by 4-inch diameter solid-tube drive core samples in saturated alluvium at approximately 40 ft depth intervals in the region of the borehole where approximately 8-inch drill casing is used to advance the borehole.  For example, if 8-inch drill casing is advanced to 560 ft bgs, drive core will be collected at approximately 380, 420, 480, 520, and 560 ft bgs in saturated alluvium.

  - Advance the approximately 6-inch core barrel and the approximately 8-inch drill casing to the required drive core depth.  Clean out all sediment from inside the 8-inch drill casing and remove the 6-inch core barrel.

  - Run the drive core system to the bottom of the borehole.  Apply air to the percussion hammer and steadily advance the solid tube sampler through an interval of undisturbed alluvium that exceeds the length of the core barrel and drive shoe by approximately 0.2 ft. This overdriving is required to prevent the sample from falling out of the drive core barrel.  Drive coring of the 2 ft plus interval should be completed in 1 to 2 minutes.

  - Bring the core barrel to the ground surface and remove cross-over sub from the top of the core barrel and the shoe from the bottom.

  - The NWRPO and DOE will supply and operate a hydraulic core extruder to remove core segments from the core barrel.

6.0 Borehole Geophysical Logging and Subsurface Completion

Figure 3 shows the detailed completion diagram for the dual string piezometer monitor well with approximately 9-inch conductor casing grouted in place with concrete grout in a 12¼ inch diameter borehole.  If the 9-inch conductor casing is drilled to 350 ft bgs using a method such as dual rotary, Figure 3 would be modified to show the 9-inch conductor casing in contact with the formation below 60 ft, and to show the 60 ft of permanent surface casing in the upper portion of the borehole.

In addition, Figure 3 may be modified by the NWRPO prior to initiating subsurface completion activities to accommodate field conditions. The target depths for all completion materials (including well casing/screen and stemming materials) must be achieved within several feet.  Thus the completion process must be conducted with extreme care including frequent tagging (i.e. measurement) of completion (stemming) material depths.  The NWRPO will supply a tagging instrument

  - When the borehole total depth of 650 ft bgs is reached or drilling and coring is terminated at a shallower depth because it is not feasible to proceed deeper, remove the core barrel from the borehole and standby while borehole geophysical logging is conducted inside the drill casing(s) by other NWRPO contractors.

  - Upon completion of borehole geophysical logging, retract 8-inch and/or 5.5-inch drill casing to approximately 530 ft bgs.

  - Run an approximately 1 ½-inch diameter steel temmie to the bottom of hole and backfill to approximately 550 ft bgs with “bensand” grout (2:1 by weight mixture of 8/12 sand and 8 mesh bentonite [e.g. Benseal]) in 10 to 20 ft stages.  Use centrifugal pump to emplace bensand grout.  Use pumped water to carry the bensand through the tremmie.  Add the dry bensand mixture through an open “T” connection on the water intake side of the centrifugal pump.

  - If the borehole only contains 8-inch drill casing at 530 ft (i.e. the 5.5-inch casing is not present), run in dual string piezometer casing/screen (2-inch Schedule 80 PVC) to approximately 550 ft bgs as shown in Figure 3.  The upper and lower piezometers strings shall be strapped together. Attach centralizers above and below each well screen.  Use tremmie pipe and centrifugal pump as described previously to emplace the sandpack and bensand grout as shown in Figure 3.  Emplace high solids bentonite grout interval with a standard grout pump, and the fine particle size dry bentonite seal in the upper 50 ft of borehole by gravity free-fall methods.

To minimize the potential for the borehole to cave on the dual string piezometer during the emplacement of stemming materials below 350 ft (i.e. the bottom of the 9-inch conductor casing), pull the 8-inch drill casing back in 10 to 30 ft stages.  Following each pull back, the bottom of the well will be sounded to determine if caving has occurred.  Completion materials will then be emplaced (tremmied) in each pull back interval up to a depth of approximately 5 ft below the 8-inch drill casing.

If the borehole contains 5.5-inch drill casing at 530 ft bgs, only run in the deeper piezometer string with centralizers located above and below the screen.  Emplace stemming materials to within 10 ft of the proposed bottom depth of the shallower piezometer string following methods described above and in accordance with depth intervals specified in Figure 3.  Then run in the shallower piezometer string without centralizers to 540 ft bgs.  This will be feasible because the 5.5-inch drill casing will have been removed from the borehole and there is adequate room in the 8-inch drill casing for two piezometers strings and a tremmie.

When completion materials reach the bottom of the 9-inch casing at approximately 350 ft bgs, pull all of the remaining 8-inch drill casing from the borehole and continue emplacing completion materials according to the specifications in Figure 3.

- Surface Completion

The required surface completion diagram for a borehole containing 9-inch conductor casing in a 12 ¼-inch borehole is presented in Figure 4.  If the 9-inch conductor casing is drilled in place, Figure 4 would also show a larger diameter steel surface casing terminating in the concrete pad.

  - Weld on an above ground extension to the approximately 9-inch diameter conductor casing.  The steel conductor casing should extend approximately 2 ft above the ground surface.  The 2-inch PVC blank casing should extend slightly below the surface casing.

  - Install caps on the PVC casings and a locking cap on the surface casing.

  - Install an approximately 8-inch thick concrete pad that extends approximately 4 inches below and 4 inches above ground surface.  Slope the top of the concrete pad approximately 0.25 inches per horizontal ft away from the surface casing.